# Spinr Code-Review Remediation

Master Implementation Program Plan

How we turn 301 review findings into shipped, tested fixes — in plain language and in engineering detail

## In one paragraph (for anyone)

A full review of the Spinr codebase found 301 things worth fixing — 16 that are urgent (money, security, or safety), 103 that are important, and 182 smaller gaps. This program turns that list into a plan: we fix the urgent ones first, we group the rest so one team can fix a whole pattern at once, and every fix ships with a test so the problem cannot silently come back. The work is organised into six documents — one per part of the product — that hang off this master plan.

Program totals: 301 findings · 16 Critical / 103 Major / 182 Minor.  Estimated total effort ~483.5 person-days (planning estimate, not a commitment).

## The big idea: fix patterns, not just tickets

Most findings are instances of a handful of root causes. Fixing the pattern once — a single shared piece of code — clears many findings at once and stops them recurring. These are the highest-leverage pieces of work in the whole program:

| Pattern (root cause) | Findings | Central fix (do this once) |
| --- | --- | --- |
| Swallowed / fail-open DB or auth errors (warn-and-continue) | 57 | Replace warn-and-continue with logger.error + 5xx; never fail open. |
| Receipts / tax lines do not reconcile (missing discount, wrong GST/PST) | 26 | Recompute tax at settlement; emit a discount line everywhere. |
| Filter/paginate applied after fetch; silent row caps | 16 | Push filters into the DB query; alert when a row cap is hit. |
| Stripe idempotency key omits amount / missing idempotency | 15 | Include the amount in every Stripe idempotency key. |
| Raw GPS / PII risk in logs, analytics, or third parties | 15 | One PII scrubber for logs/analytics; proxy 3rd-party calls. |
| Missing ownership check / IDOR on id-taking endpoints | 13 | A shared ownership-check helper on all id-taking endpoints. |
| Missing admin audit-log on money/config actions | 13 | One log_admin_action decorator on all admin mutations. |
| Background-loop replay hazard (flag/notify after side-effect, lock TTL) | 12 | Claim-before-side-effect; lock TTL below the tick interval. |
| Non-atomic wallet / balance writes (read-modify-write, no row lock) | 9 | One row-locking Postgres function for every balance change. |
| Insurance-period ledger not recorded / misclassified | 6 | Record a period transition on every driver state change. |

## The roadmap

- Phase 1 — Stop the bleeding (the 16 Criticals + the two central primitives they need). Target: the next release. This includes the one row-locking wallet function, the ownership-check helper, and the safety-alert import fix.

- Phase 2 — Fix the important patterns (103 Majors), batched by workstream: money & payments, rides & dispatch, drivers & insurance periods, safety & privacy, platform & loops. Target: this quarter.

- Phase 3 — Close the gaps (182 Minors), folded into normal sprints, preferably alongside a Phase-2 change touching the same file.

## The six surface plans

Each document below is a standalone plan for one part of the product, with phased work items, effort, and the exact test to add for each fix.

| Surface | Findings | Person-days | Document |
| --- | --- | --- | --- |
| Backend (FastAPI / Python) | 249 | 385.5 | Implementation_Plan_2_Backend.docx |
| Cross-Cutting / Repo-Wide | 23 | 70 | Implementation_Plan_7_Cross_Cutting.docx |
| Rider App (React Native / Expo) | 14 | 13 | Implementation_Plan_3_Rider_App.docx |
| Driver App (React Native / Expo) | 5 | 7 | Implementation_Plan_4_Driver_App.docx |
| Shared Package (@spinr/shared, TypeScript) | 5 | 5.5 | Implementation_Plan_6_Shared_Package.docx |
| Admin Dashboard (Next.js) | 5 | 2.5 | Implementation_Plan_5_Admin_Dashboard.docx |

## Dependencies & sequencing (do these in order)

- Build the one row-locking wallet/balance function FIRST, then convert all 9 non-atomic wallet sites to use it — do not fix them individually.

- Add the ownership-check helper, then apply it to the driver-cancel IDOR and every other id-taking endpoint; the insurance-period-corruption finding is resolved as a side effect once the IDOR is fixed.

- Land the central PII scrubber before the individual log/analytics compliance items, so each becomes a one-line adoption.

- Fix the corporate-billing sign error (allowance rides currently credit instead of charge) with a migration + backfill/audit of existing balances — schedule the balance audit alongside the code fix.

- Restore the safety-team alert import (one-line, but P0) before anything else in Safety — it currently fails silently in production.

## Governance & definition of done

- Every fix is one logical change (≤ ~200-line diff), with a regression test, reviewed; money/auth/safety changes need a second reviewer.

- New state transitions, fare branches, and auth/RLS paths must have tests (both allowed and denied paths).

- Schema changes are append-only new migrations shipping RLS in the same file and safe against live traffic.

- Background-loop changes stay replay-safe (atomic claim / idempotency key / claim flag) because every loop runs on every replica.

- Deploy to Fly.io + Railway in parallel; wrap risky behavioural changes behind a flag; watch reconciliation after money changes.

## Exit criteria for the program

- All 16 Criticals fixed, tested, and verified in production behaviour.

- Each of the 10 systemic patterns has a single central fix in place and the individual sites converted.

- No open P0/P1 without either a merged fix or a written, accepted risk decision.

- A short regression suite exists for every money, auth, safety, and insurance-period path touched.

## Companion artifacts

- SPINR_CODE_REVIEW.md — the full technical findings report.

- Spinr_Code_Review_Report.docx — the same findings as a plain-language matrix.

- Spinr_Code_Review_Matrix.csv — filterable tracking sheet (assign owners, set status).

- The six surface implementation plans listed above.