# Implementation Plan

Backend (FastAPI / Python)

Part of the Spinr code-review remediation program · plain-language + technical

## What this surface is

The backend is the brain of Spinr — it runs booking, dispatch, payments, driver management, safety, and every rule the apps depend on. It holds the largest share of findings because it holds the most logic.

Scope: 249 findings — 10 Critical, 83 Major, 156 Minor.  Estimated effort ~385.5 person-days.  Suggested lead: Platform + domain squads.

How to read the plan: Work is split into three phases by urgency — Phase 1 (P0, fix now), Phase 2 (P1, this cycle), Phase 3 (P2, backlog). Within each phase, items are grouped into workstreams so one squad can own a related batch. Effort: S ≈ half a day, M ≈ two days, L ≈ a week. Every item lists the specific regression test to add — no fix ships without one.

Verification caveat: Critical items were re-checked against source during the review. Confirm each Major/Minor against the cited file before starting, in case the surrounding code has shifted.

## Phase 1 · Critical (P0) — fix before the next release — 10 items · ~23 person-days

These can cause money loss, data exposure, or safety/regulatory failure during normal operation. They are release-blockers and should be scheduled first, with a regression test and a code review each.

### Workstream: Drivers & Insurance Periods (3)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-003 | Critical P0 | Standard payout: TOCTOU balance race and no compensation if DB insert fails after Stripe transfer File: backend/routes/drivers/payouts.py:590 Fix: Reserve the amount atomically first (insert the payouts row status='pending' before the transfer, or use a DB-side claim like corporate_wallet_apply_delta), transfer second, and reverse the transfer if the terminal write fails, as the instant path does. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-004 | Critical P0 | Any driver can cancel any other user's pre-trip ride (no ownership check) File: backend/routes/drivers/ride_cancel.py:79 Fix: Reject with 403/404 when ride['driver_id'] != driver['id'] (allow only the assigned driver), and include driver_id in the atomic cancel filter. | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-005 | Critical P0 | Active-ride rider object leaks password_hash, fcm_token and other users-row secrets to the driver app File: backend/routes/drivers/ride_reads.py:149 Fix: Switch to an allowlist projection (e.g. first_name, photo_url, rating, id) instead of a three-field blocklist. | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |

### Workstream: Rides & Dispatch (3)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-006 | Critical P0 | Booking-time card pre-auth hold is never released on cancellation; fee charge overwrites the hold's PI reference File: backend/routes/rides/cancellation.py:268 Fix: In cancel_ride_rider and ride_search_timeout, before overwriting any payment fields, read the ride's payment_intent_id/auth_status and call cancel_authorization(ride_id, payment_intent_id) when auth_status is 'authorized'/'fare_only', then set auth_status='released'. Store the cancellation-fee PI in a separate column (e.g. cancel_fee_payment_intent_id) instead of overwriting payment_intent_id. Add a reconciliation sweep for cancelled rides with auth_status still open. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-007 | Critical P0 | Mid-trip stop add/remove never recomputes grand_total, taxes, or the fare snapshot — the amount actually billed never changes File: backend/routes/rides/stops.py:70 Fix: In _reestimate_fare_for_stops (or the stops endpoints), recompute area fees and taxes via calculate_all_fees on the new total_fare, write updated tax_amount/tax_breakdown/grand_total and driver_earnings/admin_earnings, and refresh fare_breakdown_snapshot (or mark it invalidated) in the same update. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-008 | Critical P0 | /rate credits unbounded, uncharged tips into driver_earnings on every call File: backend/routes/rides/rating.py:64 Fix: In rate_driver: (1) reject the request (or ignore the tip) if ride.rider_rating is already set or ride.tip_amount > 0 (mirror ERR_TIP_DUPLICATE); (2) add le=500 to RideRatingRequest.tip_amount in schemas.py; (3) only record the tip when payment_status is still pending/failed (i.e. it will be collected by process-payment), otherwise return a structured error directing the client to the charged tip flow; (4) add @idempotent_endpoint(scope="ride_rate"). | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |

### Workstream: Auth & Identity (1)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-001 | Critical P0 | Circuit-breaker half-open probe leaks permanently on deadline abort, wedging every DB call in 503 File: backend/repositories/_base.py:228 Fix: Wrap the probe accounting in a try/finally: on any exit from run_sync after should_allow() returned True in half-open (or open→half_open) state without a definitive success, call _breaker.record_failure() (returns state to open with a fresh OPEN_DURATION). Simplest: add a `_breaker.release_probe()` that clears _probe_in_flight, and call it from the deadline-timeout / deadline-exhausted / ValueError early-exit paths. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |

### Workstream: Platform, Loops & Realtime (1)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-002 | Critical P0 | Unverified email accepted at profile creation is trusted as a corporate-billing identity File: backend/routes/users.py:67 Fix: Require email ownership verification (send a code/link, e.g. reuse the existing hash_otp email-OTP machinery) before persisting users.email, or at minimum store an email_verified flag and make /corporate/join-domain and /auth/verify-email-otp only trust verified emails. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |

### Workstream: Safety, Privacy & Reporting (1)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-009 | Critical P0 | Safety-team notification dead in production: notify_safety_team missing from fallback import branch File: backend/routes/safety.py:24 Fix: Add `from features import notify_safety_team` to the except branch (and add a regression test that imports routes.safety in top-level mode and asserts notify_safety_team is bound). | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |

### Workstream: Money & Payments (1)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-010 | Critical P0 | Allowance-covered ride settlement CREDITS the corporate master wallet instead of debiting it File: backend/services/payment_service.py:419 Fix: Introduce a proper 'ride_debit' path: call corporate_wallet_apply_delta with type='ride_debit', delta=-allowance_debit, ride_id set, plus a member-scoped used+=allowance_debit update in one RPC (extend migration 29 with a 'ride_debit' branch: master -p_amount, used +p_amount). Reserve 'allowance_rollback' for genuine grant undo. Backfill/audit existing corporate wallet balances. | L (~1 week) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |

## Phase 2 · Major (P1) — this cycle — 83 items · ~184 person-days

Real defects that will surface under load, edge cases, or specific flows. Batch them by workstream so a squad fixes a whole pattern at once.

### Workstream: Money & Payments (21)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-060 | Major P1 | valid_from, valid_days, valid_hours, applicable_areas, user_segments accepted at creation but never enforced at redemption File: backend/routes/admin/promotions.py:44 Fix: Enforce valid_from, valid_days/valid_hours (in area local time), and applicable_areas in _validate_promo_for_user and list_available_promos, or reject those fields at creation until they are enforced. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-061 | Major P1 | Insert-failure fallback silently strips private-promo targeting fields File: backend/routes/admin/promotions.py:233 Fix: Only fall back on a missing-column error (inspect the PostgREST error code), otherwise re-raise; if the fallback is taken, fail loudly or return a warning that the targeting fields were not stored. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-062 | Major P1 | Manual surge override above 2.5 is silently clamped in fare paths while dashboards show the raw value File: backend/routes/fares.py:235 Fix: Either honour manual surge_source up to the validated 10.0 in the fare paths (cap only auto), or reject admin values above 2.5 outright — and make get_surge_status report the effective (charged) multiplier in either case. | M (~2 days) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-063 | Major P1 | total_budget cap is dead — budget_used is never incremented File: backend/routes/promotions.py:237 Fix: Increment budget_used atomically (RPC like increment_promo_uses, e.g. UPDATE promotions SET budget_used = budget_used + :discount WHERE id = :id AND (total_budget = 0 OR budget_used + :discount <= total_budget) RETURNING) inside _record_promo_application, and 409 when the budget is exhausted. | L (~1 week) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-064 | Major P1 | POST /promo/apply consumes the promo but never discounts the ride File: backend/routes/promotions.py:341 Fix: Have apply_promo persist subtotal_fare/discount_amount/promo_code/promo_application_id/grand_total on the ride exactly like rides/booking.py:940-950, reject rides that already have promo_application_id set or are past in_progress, and pass ride.grand_total (not total_fare) for free_ride promos — or remove the endpoint if booking-time application is the only supported flow. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-065 | Major P1 | Tax not recalculated when fare is recalculated at completion — GST/PST receipt lines wrong File: backend/services/fare_service.py:386 Fix: Recompute area fees and GST/PST from the recalculated taxable base inside recalculate_fare_for_distance (using the booking-time rates stored on the ride) and return the new tax_amount/area totals with the adjustment. | M (~2 days) | Add a case asserting the correct insurance-period / tax line / receipt figure; update the state-machine test if a transition changes. |
| SPINR-066 | Major P1 | Quest expiry uses raw string comparison — crashes on NULL end_date and expires offset-timezone quests early File: backend/utils/quest_tracker.py:90 Fix: Reuse quests.py's _parse_dt: parse end_date to a tz-aware datetime, treat None as open-ended, and compare datetimes. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-067 | Major P1 | Referral kind inferred from 'RIDE' code prefix — custom rider referral codes are never paid File: backend/utils/referral_payout.py:201 Fix: Store an explicit referral kind (or the referrer's user id + kind) on the referee row at application time and dispatch on that, instead of inferring from the code prefix; backfill and alert on referees whose kind resolution currently dead-ends. | L (~1 week) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-068 | Major P1 | confirm_payment strands ride in payment_status='processing' with no release on failure File: backend/routes/payments.py:391 Fix: On any exception after the claim, atomically reset payment_status processing->pending (mirroring auto_settle_guest_corporate's release), and/or persist payment_intent_id onto the ride before the Stripe retrieve so retry/heal paths can recover it. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-069 | Major P1 | confirm_payment writes raw Stripe intent.status ('succeeded') into ride.payment_status instead of 'paid' File: backend/routes/payments.py:471 Fix: Map intent.status=='succeeded' to payment_status='paid' (plus paid_at), map non-terminal statuses back to 'pending'/'failed' rather than writing raw Stripe vocabulary, and update the test. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-070 | Major P1 | charge.refunded marks ride fully 'refunded' on any partial refund File: backend/routes/webhooks.py:851 Fix: Compare amount_refunded to the charge's captured amount; set payment_status='refunded' only when fully refunded, otherwise a 'partially_refunded' state (or keep 'paid') while still recording refund_amount and the ledger reversal. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-071 | Major P1 | invoice.paid/payment_failed read top-level invoice.subscription, removed in the pinned Basil API version File: backend/routes/webhooks.py:1131 Fix: Add a Basil-aware extractor mirroring _extract_invoice_payment_intent: try invoice['subscription'], then invoice['parent']['subscription_details']['subscription'], then an expanded Invoice.retrieve fallback; use it in both invoice.paid and invoice.payment_failed. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-072 | Major P1 | record_payment_event has no idempotency key — financial_events can be double-written File: backend/services/payment_service.py:127 Fix: Add a unique index on financial_events (event_type, ride_id, ref) (ref = payment_intent_id) and make record_payment_event insert-ignore-conflict, or dedupe inside the function before insert. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-073 | Major P1 | Idempotency decorator caches non-dict returns (402 JSONResponse) as HTTP 200 with a repr-string body File: backend/utils/idempotency.py:217 Fix: Detect Response/JSONResponse results: cache their real status_code and decoded body (or skip caching non-2xx), never hard-code 200. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-074 | Major P1 | Stranded-hold capture collects the tip from the rider but never credits it to driver_earnings File: backend/utils/payment_retry.py:445 Fix: Merge `**_tip_ride_update(ride, tip_d)` into the paid-write in the requires_capture branch. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-103 | Major P1 | allowance_reset destroys granted-but-unspent funds without crediting master File: backend/migrations/29_corporate_allowance_rpc.sql:72 Fix: In the allowance_reset branch, when v_used < 0 credit the master wallet with -v_used (return the unspent earmark): `v_master_delta := GREATEST(-v_used, 0)`, keeping v_used_delta := -v_used, and write both ledger rows. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-104 | Major P1 | Hard delete of a corporate account cascades away the entire financial ledger File: backend/routes/corporate_accounts.py:657 Fix: Replace hard delete with the existing status transition to 'closed' (soft delete); restrict physical deletion to accounts with zero wallet transactions, or archive ledger rows to an audit table before delete. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-105 | Major P1 | Allowance-request approval is not atomic — concurrent approvals double-grant File: backend/routes/corporate_company.py:358 Fix: Claim the request atomically first: UPDATE corporate_allowance_requests SET status='approved', reviewed_by=?, reviewed_at=now() WHERE id=? AND status='pending' RETURNING *; only apply_grant when the claim returned a row (and on grant failure flip the row back to pending/failed). | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-106 | Major P1 | auto_approve_monthly_count cap never enforced — auto_approved_this_period is never incremented File: backend/routes/corporate_rider.py:240 Fix: Atomically increment auto_approved_this_period as part of the auto-approve claim (UPDATE corporate_member_allowances SET auto_approved_this_period = auto_approved_this_period + 1 WHERE id=? AND auto_approved_this_period < ? RETURNING *) before inserting the auto_approved request and applying the grant; fall back to a pending request when the claim returns zero rows. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-107 | Major P1 | Auto-approved request row is written before (and survives without) the grant File: backend/routes/corporate_rider.py:247 Fix: Insert as pending, apply the grant, then flip to auto_approved on success (or approve atomically with the grant); on grant failure mark the request denied/failed with the floor error so the member and admin see the true state. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-108 | Major P1 | Policy evaluation is fail-open on DB errors — spend caps silently bypassed File: backend/services/corporate_policy_service.py:113 Fix: Distinguish 'no policy configured' (pass) from 'policy fetch failed' (raise or return a blocking PolicyResult with a policy_unavailable failed_rule); at minimum use logger.error and a metric, and let callers decide whether to block or allow with an explicit flag. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |

### Workstream: Platform, Loops & Realtime (14)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-030 | Major P1 | Watchdog registration and heartbeat coverage gaps leave many loops unmonitored File: backend/core/lifespan.py:434 Fix: Make registration self-derive from _spawn (register every spawned name), add record_heartbeat calls to subscription_expiry, t4a, push_retry, fix safety_checkin's name to match, and add a test asserting the watchdog list equals the spawned-loop set. | M (~2 days) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-031 | Major P1 | Expired-document suspension has no active-ride guard and writes no insurance-period transition File: backend/utils/document_expiry.py:147 Fix: Skip (and log) drivers linked to an active ride, deferring suspension to trip end; on a successful offline flip, call record_period_transition(driver_id, 0) as the stale-intent path does. | M (~2 days) | Add a case asserting the correct insurance-period / tax line / receipt figure; update the state-machine test if a transition changes. |
| SPINR-032 | Major P1 | Synchronous Stripe SDK calls inside async background loops block the event loop File: backend/utils/payment_retry.py:331 Fix: Wrap every Stripe SDK call in these loops in `await asyncio.to_thread(...)` (or a dedicated executor), especially the paginated list iterations in the two reconcile jobs. | M (~2 days) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-033 | Major P1 | Reconciliation compares ALL succeeded Stripe PIs against only 'stripe_charge' financial_events — guaranteed false discrepancy alerts File: backend/utils/reconciliation.py:133 Fix: Filter the Stripe sum to ride-charge PIs (exclude the known non-ride metadata scopes, as stripe_reconcile already does) or widen the financial_events sum to include the corresponding top-up/subscription event types. | M (~2 days) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-034 | Major P1 | Daily Stripe reconciliation crashes on every month-end date File: backend/utils/reconciliation.py:155 Fix: Use `day_end = (datetime(date.year, date.month, date.day, tzinfo=timezone.utc) + timedelta(days=1)).isoformat()`, and claim the lock only after a successful run (or delete it on failure) so a failed day can retry. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-035 | Major P1 | Top-level import fallback omits notify_safety_team — safety team never paged on escalation File: backend/utils/safety_checkin_loop.py:40 Fix: Add `from features import notify_safety_team` (and the socket manager import) to the fallback branch; add a regression test that imports the module in top-level mode and asserts notify_safety_team resolves. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-036 | Major P1 | Safety check-in timer keys off the wrong column and resets on every ride update File: backend/utils/safety_checkin_loop.py:93 Fix: Change line 93 to `ride.get("started_at")` (or select `ride_started_at` and read that), and never fall back to updated_at for the trip-start time. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-037 | Major P1 | stripe_reconcile fetches an unordered first-2000 slice of all paid rides ever, breaking reconciliation at scale File: backend/utils/stripe_reconcile.py:162 Fix: Push the date window into the query (`ride_completed_at gte/lte yesterday`) with an `order="ride_completed_at"` and paginate; alert if the day's row count hits the limit. | M (~2 days) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-038 | Major P1 | T4A annual batch consumes its once-per-year Redis claim before doing the work — one failure loses the whole year File: backend/utils/t4a_annual_job.py:92 Fix: Replace the Redis-only claim with a durable DB claim flag (e.g. a t4a_issuance_runs row keyed on tax year, claimed atomically), release/skip-set it on failure so the next tick retries, and widen the trigger window (e.g. 'any day from Feb 28 while the year's flag is unclaimed'). | M (~2 days) | Add a case asserting the correct insurance-period / tax line / receipt figure; update the state-machine test if a transition changes. |
| SPINR-039 | Major P1 | Email-OTP login matches accounts by unverified users.email — account pre-claim takeover File: backend/routes/auth.py:492 Fix: Only allow email-OTP login to match accounts whose email was set through a verified flow (email_verified flag), and require email verification when users.email is changed via /users/profile. | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-040 | Major P1 | Corporate email OTP is 4 digits with no brute-force lockout File: backend/routes/auth.py:658 Fix: Add a per-email failure counter mirroring _record_otp_failure/_check_otp_lockout (or an attempts column on the OTP row, invalidating it after ~5 wrong guesses), and consider 6-digit codes for the email flow. | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-041 | Major P1 | Recycled phone number can reactivate a stranger's deleted account for up to 7 years File: backend/routes/auth.py:885 Fix: Gate reactivation after a dormancy threshold (e.g. >90 days since deletion request) behind an additional factor — the account's verified email, last payment card digits, or support review — rather than phone OTP alone. | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-042 | Major P1 | Account deletion deletes driver_documents by the wrong key — documents survive deletion File: backend/routes/users.py:236 Fix: Look up the driver row first (`driver = await get_driver_by_user_id(user_id)`) and delete driver_documents where driver_id == driver['id']; add a regression test asserting documents are gone after account deletion. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-043 | Major P1 | Phone number change requires no OTP verification and no E.164 normalization File: backend/routes/users.py:268 Fix: Require an OTP sent to the NEW number before committing the change (standard Uber/Lyft flow), and run validate_phone to store the normalized E.164 value. | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |

### Workstream: Rides & Dispatch (14)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-044 | Major P1 | Reaper re-dispatches rides it lost the offer claim on, racing the in-process batch handler into double-offering File: backend/utils/offer_expiry_reaper.py:117 Fix: In the reaper, only re-dispatch rides where at least one claim was won (zip results with offers and build the ride set from wins); additionally guard match_driver_to_ride with a short-TTL Redis SET NX per-ride dispatch lock (e.g. spinr:dispatch_lock:{ride_id}, ~5s) so concurrent re-dispatchers collapse to one attempt. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-082 | Major P1 | _reestimate_fare_for_stops drops the airport surcharge and the minimum-fare clamp from the recomputed total File: backend/routes/rides/_shared.py:216 Fix: Include `_d(ride.get("airport_fee", 0) or 0)` in new_total and apply the minimum-fare clamp (fetch minimum_fare from the fare config or persist it on the ride row at booking) before writing estimated_fare/total_fare. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-083 | Major P1 | Geofence and estimate rejection logs write raw GPS coordinates (PIPEDA violation) File: backend/routes/rides/booking.py:450 Fix: Log a geohash/rounded area (e.g. 2-decimal ≈ 1km) or just the service-area count and ride/rider correlation id, mirroring the matching.py fix. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-084 | Major P1 | Surge can be bypassed on an immediate ride by sending is_scheduled=true with no scheduled_time File: backend/routes/rides/booking.py:590 Fix: Key the surge exclusion on `_is_deferred_schedule` (scheduled_time present) instead of `body.is_scheduled or body.scheduled_time`, or add a model validator rejecting is_scheduled=True without scheduled_time. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-085 | Major P1 | Pre-auth hold is orphaned when the ride insert fails after authorization (including the concurrent-duplicate idempotency path) File: backend/routes/rides/booking.py:883 Fix: Wrap the insert in try/except and on any failure (or idempotent-reuse return) call cancel_authorization(ride_id, pi) for a hold created in this request before re-raising/returning. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-086 | Major P1 | Driver cancellation-fee payout is made even when the rider fee was not collected, and an uncollected fee is never retried or blocked File: backend/routes/rides/cancellation.py:238 Fix: Record uncollected cancellation fees as a receivable (e.g. extend the unpaid-ride block to cancelled rides with payment_status='failed', or negative wallet balance), or gate/flag the driver payout for reconciliation when the rider-side charge did not succeed; return the actually-collected amount in the response. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-087 | Major P1 | _offer_timeout_handler reverts the ride to searching with an unconditional id-only update, clobbering a concurrent accept File: backend/routes/rides/matching.py:1027 Fix: Make the revert conditional — `update_one("rides", {"id": ride_id, "status": RideStatus.DRIVER_ASSIGNED, "driver_id": driver_id}, ...)` — and skip the driver-release/miss-streak/notify side effects when zero rows match. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-088 | Major P1 | ride_search_timeout cancels with a non-atomic id-only update, racing a last-second driver accept File: backend/routes/rides/matching.py:1296 Fix: Use a conditional claim: `update_one("rides", {"id": r_id, "status": RideStatus.SEARCHING}, base_update)` and only emit the cancellation events when a row was claimed. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-089 | Major P1 | Rate-limit decorators on all rides read endpoints are applied above @router.get and are therefore dead File: backend/routes/rides/queries.py:41 Fix: Move @ride_read_limit below @router.get on all four endpoints and add a limiter to get_rider_stats; consider a regression test asserting the registered endpoint function is the rate-limit wrapper. | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-090 | Major P1 | POST /rides/{id}/tip credits the driver a tip that is never collected from the rider File: backend/routes/rides/payments.py:113 Fix: Make add_tip actually settle the tip: charge the saved card via an off-session PaymentIntent (or debit the wallet via the idempotent RPC) and only write tip_amount/driver_earnings after the charge succeeds; alternatively disable the endpoint until a charge path exists, since process-payment already handles tips on the normal flow. | L (~1 week) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-091 | Major P1 | Re-rating the same ride re-enters the rolling average, letting one rider skew a driver's rating File: backend/routes/rides/rating.py:94 Fix: Reject (or make idempotent) a second rating: `if ride.get("rider_rating") is not None: raise HTTPException(400, "ERR_ALREADY_RATED")` before updating; for the aggregate, prefer an atomic SQL update (rating = (rating*total_ratings + :new)/(total_ratings+1), total_ratings = total_ratings+1) to also close the concurrent lost-update. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-092 | Major P1 | Cancelled-ride receipt shows the full booked fare, taxes, and grand_total instead of the cancellation fee actually charged File: backend/routes/rides/receipts.py:84 Fix: For status==cancelled, build the breakdown from the cancellation fee only (one 'Cancellation fee' line plus its actual tax treatment, if any) and set grand_total to cancellation_fee_admin + cancellation_fee_driver (0 when no fee was charged); compute any fallback sum with _d()/_round() instead of float addition. | M (~2 days) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-093 | Major P1 | SOS SMS falsely tells emergency contacts 'Location shared with emergency services' File: backend/routes/rides/safety.py:118 Fix: Change the copy to be truthful, e.g. " Their live location has been shared with Spinr's safety team." — never reference 'emergency services' as already having the location; keep the existing 'Call them or emergency services immediately' call to action. | M (~2 days) | Add a case asserting the correct insurance-period / tax line / receipt figure; update the state-machine test if a transition changes. |
| SPINR-094 | Major P1 | Share tokens created via GET /share never get a creation timestamp, so they never expire File: backend/routes/rides/sharing.py:57 Fix: Set shared_trip_token_created_at in the GET handler exactly as the POST handler does, and in track_shared_ride treat a missing/malformed timestamp on an ended ride as expired (fail closed) instead of allowing access; backfill created_at for existing tokens or null out tokens on ride completion. | L (~1 week) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |

### Workstream: Drivers & Insurance Periods (12)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-048 | Major P1 | _ride_income treats tips inconsistently: canonical path excludes tip, legacy fallback includes it File: backend/routes/drivers/_shared.py:108 Fix: Make the fallback match the canonical definition (drop tip_amount from it, report tips separately) or consistently add tips in both branches, and pick one for the T4A. | M (~2 days) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-049 | Major P1 | payable_balance formula diverges from earnings screen and canonical driver_earnings File: backend/routes/drivers/earnings.py:55 Fix: Compute payable_balance from the same income definition as /earnings (_ride_income + incentives + cancel fees + bonuses [+ tax pass-through]) so drivers can withdraw exactly what they are shown. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-050 | Major P1 | v2 location-batch path skips GPS-spoofing checks — mocked fixes update the live driver marker File: backend/routes/drivers/location.py:151 Fix: Run check_location_integrity (or at minimum reject mocked=true and teleport-implausible points) before using a v2 point for the live drivers-row marker update. | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-051 | Major P1 | Vehicle-field profile edit mid-trip forces the driver offline and records insurance period 0 with a passenger aboard File: backend/routes/drivers/profile.py:195 Fix: Reject (409) vehicle/document edits while the driver has an active ride or pending offer; only then apply the needs_review + offline transition. | M (~2 days) | Add a case asserting the correct insurance-period / tax line / receipt figure; update the state-machine test if a transition changes. |
| SPINR-052 | Major P1 | decline_ride accepts any searching/driver_assigned ride and force-sets the caller available, breaking offer-claim parking File: backend/routes/drivers/ride_flow.py:448 Fix: Require a pending ride_offers row or ride.driver_id == driver.id before processing the decline; only release availability when no other claim exists; for a direct-assigned ride, atomically revert status to searching and clear driver_id. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-053 | Major P1 | Pickup OTP: crashes on NULL stored OTP, matches empty-vs-empty, and has no brute-force limiter File: backend/routes/drivers/ride_flow.py:652 Fix: Use `ride.get("pickup_otp") or ""` and reject when the stored OTP is empty; add min_length=4 to RideOTPRequest; add a Redis attempt counter with lockout per ride. | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-054 | Major P1 | Non-active driver with is_verified=True can go online (rejected/pending statuses pass the gate) File: backend/routes/drivers/status.py:171 Fix: Unconditionally reject go-online for any status other than 'active' (drop the is_verified escape hatch). | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-055 | Major P1 | Driver can go offline while in driver_assigned state — insurance period 0 recorded while obligated (Period 2) File: backend/routes/drivers/status.py:190 Fix: Include DRIVER_ASSIGNED in the offline-block query (or auto-decline/release the assignment first) so period 0 is never opened while a ride obligation exists. | M (~2 days) | Add a case asserting the correct insurance-period / tax line / receipt figure; update the state-machine test if a transition changes. |
| SPINR-056 | Major P1 | driver_documents fetch failure silently disables document-expiry gating on go-online File: backend/routes/drivers/status.py:226 Fix: On lookup failure raise 503 (fail closed) or at minimum logger.error and refuse go-online when legacy expiry columns are also empty. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-057 | Major P1 | Recurring Spinr Pass checkout charges the pre-tax plan price — GST/PST never collected on renewals File: backend/routes/drivers/subscriptions.py:545 Fix: Attach Stripe Tax (or a tax-inclusive Price validated against plan price + tax) to subscription-mode sessions, or require recurring Prices to equal the tax-inclusive total and record the tax split in subscription_payments. | M (~2 days) | Add a case asserting the correct insurance-period / tax line / receipt figure; update the state-machine test if a transition changes. |
| SPINR-058 | Major P1 | T4A summary omits incentives/bonuses/cancel fees and attributes income by booking date, not completion date File: backend/routes/drivers/tax_exports.py:45 Fix: Include all platform-paid amounts (bonuses, incentives, cancel fees) in the T4A total and window the year on ride_completed_at (ideally in the driver's local timezone). | M (~2 days) | Add a case asserting the correct insurance-period / tax line / receipt figure; update the state-machine test if a transition changes. |
| SPINR-059 | Major P1 | PIPEDA data export reads nonexistent 'driver_payouts' table — payout history missing or whole export fails File: backend/routes/drivers/tax_exports.py:623 Fix: Query the 'payouts' table in the export, and make the background task notify the user (or retry) on failure instead of only logging. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |

### Workstream: Admin API (9)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-017 | Major P1 | Driver 'reject' action accepted by the request model but has no handler branch — always 400 File: backend/routes/admin/drivers.py:1392 Fix: Add an `elif req.action == "reject":` branch that sets status='rejected' (or 'needs_review'), stores rejection_reason, and requires a reason like suspend/ban. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-018 | Major P1 | Broadcast notification awaits up to 10,000 sequential pushes inside the request handler File: backend/routes/admin/faqs.py:166 Fix: Fan out via BackgroundTasks with bounded concurrency (mirror messaging._fan_out), or delegate this endpoint to the cloud-messaging path. | M (~2 days) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-019 | Major P1 | ToS/Privacy edits overwrite content in place with no version history and no audit log File: backend/routes/admin/legal_documents.py:58 Fix: Append a new versioned row per edit (keep old rows immutable), add a unique constraint on (audience, doc_type, version), and log_admin_action with the admin actor. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-020 | Major P1 | Driver daily rollup discovers online drivers from only the first 10k GPS points of the day File: backend/routes/admin/maintenance.py:176 Fix: Get distinct driver_ids via SQL (SELECT DISTINCT driver_id ... or an RPC) instead of fetching raw rows, mirroring the existing compute_driver_phase_distances server-side approach. | L (~1 week) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-021 | Major P1 | Marketing suppression deletion claims to be audited but writes no audit row File: backend/routes/admin/messaging.py:477 Fix: Log an audit row (actor, channel, masked target, original suppression reason) before deleting, and consider restricting bounce/complaint-sourced deletions to super_admin. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-022 | Major P1 | Admin force-cancel allows cancelling an in_progress ride, violating the ride state machine File: backend/routes/admin/rides.py:404 Fix: Reject cancellation when status == 'in_progress' (offer force-complete instead), and make the update conditional on the previously-read status so a concurrent completion wins. | M (~2 days) | Add a case asserting the correct insurance-period / tax line / receipt figure; update the state-machine test if a transition changes. |
| SPINR-023 | Major P1 | Admin cancel frees the driver without recording an insurance period transition File: backend/routes/admin/rides.py:452 Fix: Add `await record_period_transition(driver_id, 1)` to the cancel path alongside freeing the driver. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-024 | Major P1 | Deactivating the last active super_admin is not blocked — full admin lockout possible File: backend/routes/admin/staff.py:257 Fix: Apply the same active-super_admin count check when is_active=False targets a super_admin row, and reject self-deactivation. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-025 | Major P1 | DSAR status update calls nonexistent db_supabase.get_one — endpoint always 500s File: backend/routes/admin/users.py:494 Fix: Replace with `await db_supabase.find_one("data_export_requests", {"id": request_id})` and add a regression test that patches backend.db_supabase and exercises the endpoint. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |

### Workstream: Safety, Privacy & Reporting (5)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-075 | Major P1 | T4A on-demand summary buckets by created_at while annual job uses ride_completed_at File: backend/routes/drivers/tax_exports.py:45 Fix: Bucket the on-demand T4A summary by ride_completed_at (add a completed-date range filter) so it matches the annual job and reflects when income was actually earned. | M (~2 days) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-076 | Major P1 | HTML email receipt omits promo/discount line — rows exceed printed Total File: backend/utils/email_receipt.py:132 Fix: Emit a discount line (label 'Promo (code)' when promo_code present, else 'Discount') from ride['discount_amount'] before the Total, as the JSON receipt path (_build_fare_breakdown) already does. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-077 | Major P1 | PDF receipt omits promo/discount line — rows don't reconcile to total File: backend/utils/receipt_pdf.py:45 Fix: Add a negative 'Promo (code)' / 'Discount' line from ride.get('discount_amount') before the tax rows (mirroring routes/rides/_shared.py:422) so the displayed rows reconcile to the persisted grand_total. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-095 | Major P1 | DSAR deletion keeps full PII for 7 years, contradicting the documented 30-day scrub/anonymization policy File: backend/utils/retention_purge.py:16 Fix: Either restore 30-day anonymization of non-regulated PII (keeping only regulated trip/insurance linkage attributable), or obtain documented legal sign-off and update CLAUDE.md, the privacy policy, and in-app deletion copy so user-facing promises match the implemented retention. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-096 | Major P1 | Sentry scrubber misses request bodies, stack-frame locals, extra/contexts, and breadcrumb data File: backend/utils/sentry_scrub.py:31 Fix: In sentry_sdk.init set include_local_variables=False and max_request_body_size='never' (or extend scrub_event to walk exception.values[].stacktrace.frames[].vars, event['request']['data'], event['extra']/'contexts', and scrub_breadcrumb to walk crumb['data']). | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |

### Workstream: Auth & Identity (4)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-026 | Major P1 | App Check enforcement (ENV=production) breaks the public trip-share tracking page File: backend/core/middleware.py:85 Fix: Add `/api/v1/rides/track/` to _APP_CHECK_EXEMPT_PREFIXES (the endpoint is already authorised by the unguessable share token), and add a regression test asserting a token-less GET to /api/v1/rides/track/x passes App Check in enforcement mode. | M (~2 days) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-027 | Major P1 | RelativeRedirectMiddleware rewrites legitimate external redirects (Supabase signed Storage URLs) into broken same-host paths File: backend/core/middleware.py:694 Fix: Only strip scheme+host when the Location host matches the request host (or a configured internal host list): `parsed = urlparse(location); if parsed.netloc in {request.url.netloc, <internal hosts>}: relativize`, otherwise leave the absolute URL untouched. | L (~1 week) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-028 | Major P1 | DeadlineMiddleware trusts the client clock — a device with a skewed clock gets 503 on every request File: backend/core/middleware.py:731 Fix: Clamp server-side: if remaining_ms <= 0 (or absurdly small/large, e.g. outside 0..120000), treat the header as skewed and either ignore it or floor remaining to a sane minimum (e.g. min 2s, max the known client timeout). The request's arrival itself proves the client had not given up at send time. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-029 | Major P1 | redis_client only reads REDIS_URL from the environment — a deploy configured with RATE_LIMIT_REDIS_URL/WS_REDIS_URL alone silently runs OTP lockout, SMS caps, caches, and leader locks in-process File: backend/utils/redis_client.py:80 Fix: In _get_redis(), fall back through REDIS_URL → RATE_LIMIT_REDIS_URL (matching the documented chain), or make _validate_production_config require REDIS_URL itself in production. Also log at ERROR (not silently) when production ENV runs on the in-process fallback. | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |

### Workstream: Support & Integrations (4)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-099 | Major P1 | Resolving with resolution='approved' but no refund_amount silently issues no refund File: backend/routes/disputes.py:216 Fix: For resolution='approved' default refund_amount to the dispute's requested_amount (or reject the request with 400 'refund_amount required'), so an approval can never be a silent zero-dollar refund. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-100 | Major P1 | GET /favorites always returns empty list — get_rows called with unsupported 'skip' kwarg File: backend/routes/favorites.py:44 Fix: Pass offset=skip instead of skip=skip (and add desc=True for use_count ordering); remove the exception swallow so a DB failure returns 503 per CLAUDE.md instead of a silent empty list. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-101 | Major P1 | Synchronous Gemini call blocks the event loop inside an async handler File: backend/routes/support.py:122 Fix: Wrap the call in `await asyncio.to_thread(model.generate_content, scrubbed_message)` or use the async client (generate_content_async). | M (~2 days) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-102 | Major P1 | Zoho reverse-sync closes disputes without any refund, permanently blocking the refund endpoint File: backend/services/zoho_desk_integration.py:154 Fix: Exclude disputes from the auto-close list (or only auto-close disputes that already have a resolution recorded), keeping the money decision exclusively in admin_resolve_dispute. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |

## Phase 3 · Minor (P2) — backlog / opportunistic — 156 items · ~178.5 person-days

Smaller blast radius but genuine gaps. Fold these into normal sprint work, ideally alongside a Phase-2 item touching the same file.

### Workstream: Money & Payments (36)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-203 | Minor P2 | Promo update endpoints bypass the discount caps and negative-value checks enforced at creation File: backend/routes/admin/promotions.py:445 Fix: Apply the same validation on update: reject negative values, percentage > 100, flat > 500, and negative max_discount/total_budget/min_ride_fare. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-204 | Minor P2 | Fare cache grid key can straddle a service-area boundary File: backend/routes/fares.py:66 Fix: Resolve the area first and include its id (or 'none') in the cache key, or shrink the grid and accept boundary cells as uncacheable. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-205 | Minor P2 | Fare cache not invalidated on surge activation — rider can book into surge they never saw File: backend/routes/fares.py:377 Fix: Call invalidate_fare_cache() (or delete the affected area's grid keys) from the surge engine whenever an area's multiplier changes, or always cap the fare-cache TTL at 60s. | S (≤½ day) | Add a case asserting the correct insurance-period / tax line / receipt figure; update the state-machine test if a transition changes. |
| SPINR-206 | Minor P2 | Loyalty balance update is a non-atomic read-modify-write File: backend/routes/loyalty.py:162 Fix: Increment atomically (RPC: UPDATE loyalty_accounts SET points = points + :n, lifetime_points = lifetime_points + :n ... RETURNING) and derive the tier from the returned lifetime value. | L (~1 week) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-207 | Minor P2 | Malformed expiry_date silently makes a promo never expire File: backend/routes/promotions.py:127 Fix: Treat an unparseable expiry as invalid (400) or at minimum logger.error it; use parse_iso_utc like list_available_promos does. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-208 | Minor P2 | Promo application inserted before uses-increment; 409 leaves orphan row that burns the rider's per-user limit File: backend/routes/promotions.py:285 Fix: Claim capacity first (increment_promo_uses), then insert the application; or delete the application row before raising the 409. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-209 | Minor P2 | /promo/apply is not rate limited File: backend/routes/promotions.py:341 Fix: Apply the same SlowAPI limit (e.g. promo_validate_limit) to /promo/apply. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-210 | Minor P2 | Dead count_documents query in list_available_promos File: backend/routes/promotions.py:463 Fix: Delete the call (or assign and use it if it was meant for a 30-day inactivity fast-path). | S (≤½ day) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-211 | Minor P2 | Duplicate promo-code check with limit=1 plus post-filter allows duplicate global codes File: backend/routes/promotions.py:636 Fix: Query with the service_area_id-is-null condition server-side (or raise the limit and filter), add a partial unique index on (code) WHERE service_area_id IS NULL plus unique (code, service_area_id), and add the same check to admin/promotions.py. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-212 | Minor P2 | join_quest checks end_date but not start_date; tracker also ignores start_date File: backend/routes/quests.py:195 Fix: Reject joins before start_date in join_quest and skip progress increments for rides completed outside [start_date, end_date] in quest_tracker. | S (≤½ day) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-213 | Minor P2 | max_participants enforced with check-then-insert race File: backend/routes/quests.py:214 Fix: Enforce the cap atomically (e.g. a participants counter on quests with UPDATE ... WHERE participants < max_participants RETURNING, or a DB constraint), and fail closed on count errors. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-214 | Minor P2 | earnings_target quest progress accumulates money as float File: backend/utils/quest_tracker.py:104 Fix: Accumulate via Decimal(str(...)) and quantize to 2dp before the target comparison and the DB write, or compare with a half-cent tolerance. | S (≤½ day) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-215 | Minor P2 | Peak-rides window off by one hour on both edges vs its stated 7-9 AM / 5-8 PM definition File: backend/utils/quest_tracker.py:111 Fix: Use half-open ranges (7 <= hour < 9 or 17 <= hour < 20) or update the advertised window copy to match, keeping quest descriptions and payout logic consistent. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-216 | Minor P2 | Referral candidate scan capped at 10,000 users with no truncation detection File: backend/utils/referral_payout.py:151 Fix: Filter server-side to referees without a referral_payouts claim (anti-join or a processed flag), or at minimum log an error and paginate when the fetch hits the cap. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-217 | Minor P2 | Driver-side referral credit has no idempotency key — a failed credited_at mark write enables a double-pay on re-credit File: backend/utils/referral_payout.py:630 Fix: Give referral driver_bonuses a deduplicating source_id (the referral_payouts claim id + side) under the existing unique index, so any replayed credit is rejected by the DB regardless of mark-write failures. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-218 | Minor P2 | Surge demand counts in-progress/assigned rides, double-counting busy drivers and overstating surge File: backend/utils/surge_engine.py:103 Fix: Count only unmet demand ('searching', optionally recent unfulfilled requests) as demand, or include on-trip drivers in the supply denominator, so steady-state full utilisation with no queue does not surge. | S (≤½ day) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-219 | Minor P2 | surge_pricing history row inserted every 2-minute tick even when nothing changed File: backend/utils/surge_engine.py:289 Fix: Insert history only on multiplier change (plus perhaps a low-frequency heartbeat row), and/or add a retention purge for surge_pricing. | S (≤½ day) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-220 | Minor P2 | Non-ride fallback idempotency key omits the amount — two different payments in the same minute collide File: backend/routes/payments.py:224 Fix: Include the cents amount in the fallback key: f"intent-{user}-{amount}-{minute}". | M (~2 days) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-221 | Minor P2 | setup-intent returns mock client_secret in production when Stripe key is blank File: backend/routes/payments.py:493 Fix: Mirror get_cards: raise 503 when ENV=production and the key is empty; keep the mock only for dev/staging. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-222 | Minor P2 | charge.dispute.closed maps every non-'won' status (incl. warning_closed) to dispute_lost File: backend/routes/webhooks.py:1013 Fix: Map 'won' and 'warning_closed' back to 'paid'; only 'lost' to 'dispute_lost'; log-and-skip unknown statuses. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-223 | Minor P2 | Wallet debit succeeds but wallet_transactions ledger insert failure is unrecoverable File: backend/services/payment_service.py:305 Fix: Write the ledger row inside the wallet_pay_for_ride RPC transaction, or on the already-paid no-op check for and backfill a missing wallet_transactions row for the ride. | L (~1 week) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-224 | Minor P2 | In-flight idempotency lock never released — failed request blocks same-key retry with 409 for 150s File: backend/utils/idempotency.py:201 Fix: Delete the lock key in a finally block (or at least on exception) so failed attempts are immediately retryable. | M (~2 days) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-225 | Minor P2 | Crash between 'retrying' claim and release wedges the ride permanently File: backend/utils/payment_retry.py:319 Fix: Include 'retrying' (with an updated_at staleness cutoff) in the retry scan or in the stuck-processing reconciler. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-226 | Minor P2 | Retry confirm of a requires_payment_method PI omits payment_method — retries can never succeed for common declines File: backend/utils/payment_retry.py:356 Fix: Look up the rider's current default_payment_method and pass it to confirm (or fall back to charge_ride's fresh-PI path) instead of re-confirming a card-less intent. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-227 | Minor P2 | STRIPE_ORPHAN skip-list misses subscription-renewal invoice PIs and ancillary-fee PIs File: backend/utils/stripe_reconcile.py:283 Fix: Also skip PIs with metadata.source ending in '_fee', PIs whose invoice field is set (Billing-generated), and admin ride-invoice PIs (match rides.stripe_invoice_id). | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-228 | Minor P2 | Auto-heal marks stuck-processing rides paid without ensuring a financial_events ledger row exists File: backend/utils/stripe_reconcile.py:561 Fix: Before/after healing, check financial_events for (ride_id, pi_id) and insert the stripe_charge row from Stripe truth when absent. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-280 | Minor P2 | is_active filter applied after pagination with unfiltered X-Total-Count File: backend/routes/corporate_accounts.py:196 Fix: Push is_active into list_corporate_accounts_filtered as a server-side eq filter and count with the same filters (or drop the header when filters are active). | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-281 | Minor P2 | Bookings section filter applied after pagination File: backend/routes/corporate_company_bookings.py:206 Fix: Resolve the section's member_ids first and add `corporate_member_id: {"$in": [...]}` to the DB filter before pagination. | M (~2 days) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-282 | Minor P2 | join-domain bypasses company-active check enforced by the auto-match flow File: backend/routes/corporate_rider.py:150 Fix: Fetch the corporate account in do_join_domain and 403/409 unless status == 'active', matching the auto-match contract. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-283 | Minor P2 | Admin corporate-wallet money endpoints write no audit log rows File: backend/routes/corporate_wallet.py:84 Fix: Add log_admin_action calls (action=corporate_wallet_topup/adjust/config_change with amount, notes, and changed fields) to all three endpoints, following the pattern in routes/corporate_accounts.py. | M (~2 days) | Make the guard blocking and add a CI test that fails on a bad input. |
| SPINR-284 | Minor P2 | Corporate top-up Stripe errors surface as raw 500 File: backend/routes/corporate_wallet.py:143 Fix: Catch stripe.error.CardError → 402 with the decline reason, other StripeError → 502, mirroring wallet.py's handler. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-285 | Minor P2 | Top-up accepts amounts below Stripe's $0.50 CAD minimum File: backend/routes/wallet.py:112 Fix: Set a minimum (e.g. ge=Decimal("5") or at least Decimal("0.50")) on the field so the client gets a 422 with a clear message. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-286 | Minor P2 | Wallet top-up Stripe idempotency key omits the amount — second top-up in the same minute fails File: backend/routes/wallet.py:192 Fix: Include the amount in the key, mirroring the corporate endpoint: `f"wallet-topup-{user_id}-{amount_cents}-{int(time.time() // 60)}"`. | M (~2 days) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-287 | Minor P2 | Wallet ledger row written outside the debit transaction — crash loses the audit entry File: backend/routes/wallet.py:299 Fix: Move the wallet_transactions insert into the wallet_pay_for_ride Postgres function so debit and ledger row commit atomically. | L (~1 week) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-288 | Minor P2 | GET /wallet/transactions returns page length as 'total' File: backend/routes/wallet.py:362 Fix: Either drop the misleading field, return has_more via the limit+1 trick, or run a separate count query for the wallet's transactions. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-289 | Minor P2 | Month-add clamp permanently drifts allowance period anchors File: backend/utils/allowance_reset.py:55 Fix: Store the original anchor day on the allowance row (or derive it from the initial period_start) and compute each new period_end from the anchor, clamping per-month without persisting the clamp. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |

### Workstream: Platform, Loops & Realtime (27)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-161 | Minor P2 | Subscription-expiry lock TTL (6h+5min) exceeds the 6h sleep — enforcement cadence silently halves File: backend/routes/drivers/subscriptions.py:1584 Fix: Use a TTL below the sleep interval (e.g. 6h − 5min) or a per-window bucket key so exactly one replica wins each 6-hour window. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-162 | Minor P2 | Auto-topup idempotency key freezes after a declined charge — no retry for the rest of the day File: backend/utils/corporate_autotopup.py:121 Fix: Include an attempt discriminator that advances on observed failure (e.g. count of today's failed topup intents, or an hourly bucket) in the seed, and use datetime.now(timezone.utc).date() instead of date.today(). | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-163 | Minor P2 | Low-balance email uses non-atomic read-check-notify-mark with no leader lock — duplicate billing emails across replicas File: backend/utils/corporate_low_balance.py:54 Fix: Make mark_low_balance_notified a conditional claim (UPDATE ... WHERE low_balance_notified_at IS NULL OR < cutoff, returning the row) executed BEFORE send_email, mirroring the document_expiry F6 pattern. | M (~2 days) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-164 | Minor P2 | never_ticked loops are never flagged unhealthy — a loop that dies at startup is invisible forever File: backend/utils/loop_monitor.py:77 Fix: Record a registration timestamp per loop and flip never_ticked to stale/unhealthy once now - registered_at > 2× threshold, as the comment already promises. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-165 | Minor P2 | Leader-lock TTL (1.5× interval) exceeds the tick interval, degrading payment-retry cadence to ~2× the design File: backend/utils/payment_retry.py:593 Fix: Use a TTL shorter than the interval (or delete the key at end of tick, or use a per-interval bucket key as surge_engine does) in both payment_retry and scheduled_rides. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-166 | Minor P2 | Permanently failed dispatch/SOS pushes are hard-deleted from the retry queue, erasing the failure trail File: backend/utils/push_retry.py:188 Fix: Mark rows failed (e.g. `failed_at`/`failure_reason` columns) instead of deleting, increment a `spinr_push_retry_exhausted_total` metric, and let the retention purge clean old rows. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-167 | Minor P2 | Retention purge ignores its documented 03:00 UTC schedule and can skip whole days under the 23h lock File: backend/utils/retention_purge.py:268 Fix: Sleep `_seconds_until_next(3)` before the first tick and re-align each iteration to 03:00 UTC (as stripe_reconcile.py does with _seconds_until), and drop the lock TTL below the minimum inter-tick gap. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-168 | Minor P2 | 10-minute reminder uses read-then-write flag, not an atomic claim — duplicate pushes when Redis degrades File: backend/utils/scheduled_rides.py:229 Fix: Claim atomically first: `update_one("rides", {"id": ride_id, "reminder_sent": False}, ...)` and only send the push when the claim returns a row (the CLAUDE.md claim-flag recipe). | M (~2 days) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-169 | Minor P2 | Cancelled-rides counter uses the count as a label value instead of incrementing by N File: backend/utils/stuck_ride_sweeper.py:122 Fix: Increment by the ride count with no dynamic label (loop `_metric_inc` N times or use an `inc(..., value=N)` form if metrics.py supports it). | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-170 | Minor P2 | Surge leader lock silently degrades to all-replicas-leader on Redis errors, producing conflicting price writes File: backend/utils/surge_engine.py:373 Fix: Make redis_set_nx distinguish 'Redis configured but erroring' (raise or return a tri-state) from 'Redis unset', and have surge skip the write-path (keep last multiplier) rather than multi-write when leadership can't be established. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-171 | Minor P2 | Blocking firebase_admin.verify_id_token runs on the event loop for every authenticated request File: backend/dependencies/__init__.py:354 Fix: Wrap the call in `await asyncio.to_thread(...)`, and short-circuit to the JWT path first when the token header alg is HS256 (Firebase tokens are RS256) to skip Firebase entirely for Spinr JWTs. | S (≤½ day) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-172 | Minor P2 | SOS grace path accepts expired single-purpose reactivation tokens File: backend/dependencies/__init__.py:560 Fix: Add `if payload.get("purpose") == _REACTIVATION_PURPOSE: raise original` in the grace path immediately after decoding. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-173 | Minor P2 | No per-address send cap on /auth/send-email-otp — email bombing and provider spend File: backend/routes/auth.py:591 Fix: Add a per-normalized-email Redis counter with a 30s min-interval and hourly cap, mirroring _enforce_otp_send_cap. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-174 | Minor P2 | OTP consumed before user lookup — a DB blip burns the code and can exhaust the send cap File: backend/routes/auth.py:816 Fix: Defer OTP deletion (or use the mark-verified path with a short reuse window) until after the user row is resolved and the token is minted, or delete inside the success path only. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-175 | Minor P2 | Refresh mints JWTs whose session_id claim is the stored user-agent string File: backend/routes/auth.py:1528 Fix: Drop the fallback: `session_id = user.get("current_session_id") or None` and pass None through to create_jwt_token. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-176 | Minor P2 | Logout is gated behind a 3/min per-IP limit and a live access token File: backend/routes/auth.py:1567 Fix: Raise the logout limit (or key it per-user), and accept a refresh-token-only revocation path (the refresh token itself proves possession) so logout works with an expired access token. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-177 | Minor P2 | /auth/logout-all silently no-ops for admin tokens — 12h admin sessions stay valid File: backend/routes/auth.py:1655 Fix: In logout_all, branch on the caller's role: for admin roles either proxy to the admin_staff bump or return 400 directing the client to /admin/auth/logout-all — never return success without bumping any token_version. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-178 | Minor P2 | Profile-image base64 fallback can embed a multi-megabyte data-URI in the users row File: backend/routes/users.py:357 Fix: Cap the base64 fallback (e.g. reject or downscale to <100KB if compression failed), or store the fallback in a side table/column excluded from default UserProfile serialization. | S (≤½ day) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-179 | Minor P2 | Emergency-contact reads swallow DB errors and return an empty list File: backend/routes/users.py:460 Fix: Raise HTTPException(503) from both handlers on DB failure so clients retry instead of rendering a false empty state. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-180 | Minor P2 | Emergency contact phone accepted without digit/format validation File: backend/routes/users.py:480 Fix: Run validate_phone (raise 400 on failure) and store the normalized E.164 value so Twilio delivery is guaranteed addressable. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-181 | Minor P2 | Referral code resolved by contains-regex on user id can credit the wrong referrer File: backend/routes/users.py:661 Fix: Anchor the match to the id prefix (e.g. `{"$regex": f"^{suffix}"}` or an ilike 'suffix%' filter) and treat >1 match as ambiguous (reject). | S (≤½ day) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-290 | Minor P2 | location_batch rate-limiter issues one Redis INCR per point (up to ~499 serial round-trips) on the hot GPS path File: backend/routes/websocket.py:915 Fix: Add an INCRBY wrapper to redis_client and increment by len(points) in one call, so batch accounting is a single round-trip. | S (≤½ day) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-291 | Minor P2 | Empty location_batch consumes a rate-limit token and returns no ack File: backend/routes/websocket.py:937 Fix: Short-circuit empty batches before the rate-limit accounting with an immediate `{'type':'location_batch_ack','count':0}` response. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-292 | Minor P2 | ride_status_update cooldown is consumed before the authorization/ride-existence check File: backend/routes/websocket.py:1054 Fix: Only update _last_status_echo_at after the ride is found and the caller is confirmed to be a ride participant, so invalid/unauthorized messages don't burn the cooldown budget. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-293 | Minor P2 | Push retry can deliver a duplicate notification if the sent_at update fails after a successful send File: backend/utils/push_retry.py:167 Fix: Retry the sent_at write with a short bounded retry, or record delivery idempotently (e.g. a provider message-id / delivered flag checked before re-send) so a failed mark-sent cannot cause a duplicate delivery. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-294 | Minor P2 | Receipt email hardcodes PST 6% and recomputes tax, contradicting the GST-only SK tax model and the ride's stored tax_breakdown File: backend/utils/receipt_email.py:66 Fix: Delete this unused module or rewrite _build_plain_text to render tax lines from ride['tax_breakdown']/ride['tax_amount'] like utils/email_receipt.py, so the emailed receipt matches what was actually charged. | L (~1 week) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-295 | Minor P2 | Durable event not stored in replay outbox when the outbox pipeline fails, creating a reconnect gap File: backend/utils/ws_pubsub.py:216 Fix: On pipeline failure, retry the outbox rpush independently of the publish (or fail the whole publish so the caller's local-delivery fallback is used), so any event counted in the seq sequence is also recoverable on reconnect. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |

### Workstream: Admin API (26)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-125 | Minor P2 | status-override valid set disagrees with its Pydantic Literal — 'rejected' and 'needs_review' are both unusable File: backend/routes/admin/drivers.py:1536 Fix: Make the Literal and the `valid` set identical (include both rejected and needs_review, or neither). | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-126 | Minor P2 | Broadcasts are never persisted and an invalid audience silently returns success File: backend/routes/admin/faqs.py:153 Fix: Insert the notification_doc for all branches with the real sent count, and constrain audience with Literal["user","all","riders","drivers"]. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-127 | Minor P2 | Incentive claims 'total_paid' sums only the most recent 100 claims File: backend/routes/admin/incentives.py:92 Fix: Use a SQL aggregate (count + sum via RPC or count='exact') for the totals and keep the 100-row page only for the claims list; also sum with Decimal, not float. | L (~1 week) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-128 | Minor P2 | Driver-incentive CRUD (up to $500 bonuses) writes no audit_logs rows File: backend/routes/admin/incentives.py:119 Fix: Add `admin: dict = Depends(get_admin_user)` and log_admin_action to each mutating handler, and reuse the create pattern on the update model's incentive_type. | M (~2 days) | Make the guard blocking and add a CI test that fails on a bad input. |
| SPINR-129 | Minor P2 | GPS cleanup swallows delete failures and always returns counts of -1 with HTTP 200 File: backend/routes/admin/maintenance.py:80 Fix: Propagate delete failures as 503, and return real deleted counts (delete with returning/count or a count-before-delete). | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-130 | Minor P2 | GET /admin/audit-logs limit parameter is uncapped File: backend/routes/admin/maintenance.py:287 Fix: Add `ge=1, le=500` bounds to limit and `ge=0` to offset. | S (≤½ day) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-131 | Minor P2 | Recipient resolution silently truncates every audience at 10,000 users File: backend/routes/admin/messaging.py:92 Fix: Page through the users table (keyset pagination on id) until exhausted, or at minimum compare count_documents against the fetched size and fail loudly when truncated. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-132 | Minor P2 | Redis flush-prefix has no audit trail File: backend/routes/admin/monitoring.py:501 Fix: Write an audit_logs row (actor, prefix, deleted_keys) after the flush. | M (~2 days) | Make the guard blocking and add a CI test that fails on a bad input. |
| SPINR-133 | Minor P2 | Admin force-cancel writes no audit_logs row File: backend/routes/admin/rides.py:386 Fix: Call `await log_admin_action(admin_user, "force_cancel_ride", "rides", ride_id, {"reason": reason, "status_from": ride.get("status")})` after the successful update. | M (~2 days) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-134 | Minor P2 | Payout retry endpoints claim an audit trail but write no audit_logs rows File: backend/routes/admin/rides.py:3212 Fix: Emit log_admin_action('payout_retry'/'payouts_bulk_retry', ...) with payout ids and counts. | M (~2 days) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-135 | Minor P2 | vehicle_cascade_map accepted on create but silently dropped File: backend/routes/admin/service_areas.py:420 Fix: Add `"vehicle_cascade_map": area.vehicle_cascade_map` to the create doc. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-136 | Minor P2 | Surge 'history' row is updated in place, so no surge history is actually kept File: backend/routes/admin/service_areas.py:719 Fix: Always insert a new surge_pricing row (append-only) and mark previous rows inactive, or drop the 'history' claim and stop rewriting the primary key. | M (~2 days) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-137 | Minor P2 | Area fee CRUD has no audit logging and does not invalidate the fare cache File: backend/routes/admin/service_areas.py:765 Fix: Add `await invalidate_fare_cache()` and `await log_admin_action(...)` to all three handlers (add the `admin: dict = Depends(get_admin_user)` parameter to obtain the actor). | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-138 | Minor P2 | Area tax update: unbounded rates, no audit log, no cache invalidation, and 500 on unknown area File: backend/routes/admin/service_areas.py:841 Fix: Add Field(ge=0, le=100) bounds, 404 when the area row is missing, invalidate_fare_cache(), and log_admin_action with old/new rates. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-139 | Minor P2 | Credential masking leaks the first 8 characters of every secret to all settings-module admins File: backend/routes/admin/settings.py:91 Fix: Mask with a fixed placeholder plus last-4 only (e.g. '•••• 4f2a'), never a prefix of the secret. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-140 | Minor P2 | lms_api_base_url localhost exemption is a bypassable prefix check File: backend/routes/admin/settings.py:241 Fix: Parse with urllib.parse and compare `parsed.hostname in ("localhost", "127.0.0.1")` exactly. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-141 | Minor P2 | update_staff accepts an arbitrary role string File: backend/routes/admin/staff.py:264 Fix: Validate req.role against {'super_admin','operations','support','finance','custom'} and 422 otherwise. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-142 | Minor P2 | Driver-subscription list filters status in Python after a 200-row fetch File: backend/routes/admin/subscriptions.py:122 Fix: Push the status into the DB filter (`{"status": status}`) and add limit/offset pagination. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-143 | Minor P2 | Hard deletes of tickets, flags and complaints are unaudited File: backend/routes/admin/support.py:387 Fix: Prefer soft-delete (is_deleted flag) and add log_admin_action with the acting admin to all three delete handlers. | M (~2 days) | Make the guard blocking and add a CI test that fails on a bad input. |
| SPINR-144 | Minor P2 | suspended_until accepted as an arbitrary unvalidated string File: backend/routes/admin/users.py:50 Fix: Type it as Optional[datetime] (Pydantic parses/validates) and reject past timestamps. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-145 | Minor P2 | GET /admin/users limit/offset are uncapped File: backend/routes/admin/users.py:57 Fix: Bound both with Query/Field(ge=1, le=500). | S (≤½ day) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-146 | Minor P2 | User export emits columns that are never selected — city/total_rides/rating/is_verified are always empty File: backend/routes/admin/users.py:420 Fix: Drop the four dead fields from the export or join the driver/derived data before exporting. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-147 | Minor P2 | DSAR list 'total' is the page length, not the true total File: backend/routes/admin/users.py:478 Fix: Return `await db_supabase.count_documents("data_export_requests", filters)` as total. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-148 | Minor P2 | Fare-config update silently ignores minimum_fare and booking_fee; no bounds or audit on fare rates File: backend/routes/admin/vehicle_fleet.py:136 Fix: Add minimum_fare/booking_fee to the update model and handler, add ge=0 bounds on all money fields, and audit fare-config create/update/delete. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-149 | Minor P2 | AdminDebitRequest.amount is float with gt=0, allowing sub-cent amounts that quantize to $0.00 File: backend/routes/admin/wallet.py:55 Fix: Mirror the credit model: `amount: Decimal = Field(..., gt=Decimal("0.01"), le=Decimal("10000"))`. | S (≤½ day) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-150 | Minor P2 | Idempotency guard is check-then-insert — duplicate concurrent requests double-credit File: backend/routes/admin/wallet.py:123 Fix: Add a unique index on (reference_id, type) in wallet_transactions and treat the duplicate-key error as 'return existing transaction', or claim the key atomically before mutating the balance. | M (~2 days) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |

### Workstream: Rides & Dispatch (20)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-182 | Minor P2 | set_driver_available's is_online clamp is read-then-write, allowing is_available=True with is_online=False File: backend/repositories/driver_repo.py:163 Fix: Make the availability grant conditional in the write itself: `.update({"is_available": True, ...}).eq("id", driver_id).eq("is_online", True)` (keeping the release path unconditional), removing the TOCTOU window. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-183 | Minor P2 | Module-level shared Response instance reused across requests lets middleware-set headers cross-leak File: backend/routes/offer_card.py:49 Fix: Replace the shared constant with a fresh `Response(status_code=404)` constructed at each return site. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-184 | Minor P2 | Offer-card token's driver binding is never verified — documented protection is unenforced File: backend/routes/offer_card.py:67 Fix: Since the OS image fetch cannot present driver identity, either drop the 'dr' claim and correct both docstrings, or log/verify 'dr' against a pending ride_offers row for that driver as a secondary gate before rendering. | M (~2 days) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-185 | Minor P2 | Single-offer timeout path skips acceptance-rate update, diverging driver stats from the batch path File: backend/routes/rides/matching.py:986 Fix: Add `await update_acceptance_rate(driver_id, accepted=False)` after the miss-streak increment in _offer_timeout_handler, mirroring process_expired_offer. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-186 | Minor P2 | Admin driver_matching_algorithm setting (rating_based/round_robin) is silently ignored on the live dispatch path File: backend/services/dispatch_service.py:202 Fix: Either wire select_driver_by_algorithm into the batch-claim ordering in _match_driver_to_ride_attempt, or remove the rating_based/round_robin options from the admin setting and document that ordering is nearest/ETA-only. | M (~2 days) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-187 | Minor P2 | ride_search_timeout armed with bare asyncio.create_task — task can be garbage-collected mid-sleep File: backend/utils/scheduled_rides.py:210 Fix: Import and use utils.background.spawn (or _deps.spawn) instead of bare asyncio.create_task, matching the live booking path. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-188 | Minor P2 | Reminder flag written after the push with no atomic claim — duplicate reminder pushes File: backend/utils/scheduled_rides.py:243 Fix: Claim first: `update_one("rides", {"id": ride_id, "reminder_sent": False}, {"$set": {"reminder_sent": True}})` and only send the push when the claim returns a row. | M (~2 days) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-189 | Minor P2 | Leader-lock TTL (90s) exceeds the 60s tick and is never released, halving scheduled-dispatch cadence File: backend/utils/scheduled_rides.py:257 Fix: Either set the lock TTL below the tick interval (e.g. 45s) or DELETE the lock in a finally block after the tick completes so the next 60s tick can run. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-242 | Minor P2 | Wallet balance precheck uses the pre-promo grand_total File: backend/routes/rides/booking.py:642 Fix: Validate the promo (or at least compute the prospective discount) before the wallet precheck, or compare against grand_total minus the validated discount. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-243 | Minor P2 | Rider cancel records insurance Period 1 unconditionally, even if the driver is offline File: backend/routes/rides/cancellation.py:327 Fix: Capture the set_driver_available return value and only record Period 1 when the release actually landed with is_available=True, mirroring the matching.py guards. | S (≤½ day) | Add a case asserting the correct insurance-period / tax line / receipt figure; update the state-machine test if a transition changes. |
| SPINR-244 | Minor P2 | Mid-trip stops bypass all geofence and coordinate validation File: backend/routes/rides/stops.py:62 Fix: Add ge/le bounds on lat/lng in AddStopMidTripRequest and run the same _get_active_service_area_for_point gate against the new stop before accepting it. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-245 | Minor P2 | Ride-existence leak the chat-status guard closed is still open in /messages and /typing File: backend/routes/rides/chat.py:86 Fix: Return 404 for non-participants in get_ride_messages, send_ride_message, and send_typing_indicator, matching the chat-status pattern. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-246 | Minor P2 | GET /messages returns the oldest 100 messages, hiding the newest once a chat exceeds 100 File: backend/routes/rides/chat.py:89 Fix: Fetch the newest 100 (`desc=True, limit=100`) and reverse in memory before returning, or add offset-based pagination. | M (~2 days) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-247 | Minor P2 | Chat push falls back to the sender's full name in a cleartext notification File: backend/routes/rides/chat.py:185 Fix: Use the existing first_name_only helper (already imported in sibling modules) for sender_name instead of falling back to the full name field. | S (≤½ day) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-248 | Minor P2 | Rider typing indicator is sent to a WebSocket key built from drivers.id, not the driver's user_id File: backend/routes/rides/chat.py:230 Fix: Resolve the driver row once and use its user_id for the target: `drv = await _deps.db_supabase.get_driver_by_id(driver_id); target = f"driver_{drv['user_id']}" if drv and drv.get("user_id") else None`. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-249 | Minor P2 | Full free-text lost-item description is sent in the FCM push body without truncation File: backend/routes/rides/lost_found.py:82 Fix: Send a generic body (e.g. "A rider reported a lost item from a recent trip — open the app for details") or truncate to a short preview, and dispatch it via _push_in_background. | M (~2 days) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-250 | Minor P2 | Receipt payment_method field surfaces the raw Stripe payment_method_id File: backend/routes/rides/receipts.py:124 Fix: Branch on ride.payment_method ('wallet' → 'Spinr Wallet', 'company_allowance' → 'Corporate Account', else card), and for cards resolve brand/last4 from the saved payment-method record rather than echoing the Stripe id. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-251 | Minor P2 | Safety check-in 'I'm okay' is lost across replicas when Redis is unset, causing false escalations File: backend/routes/rides/safety.py:207 Fix: Have safety_checkin_response (or the loop) detect the in-memory fallback and fall back to a durable marker — e.g. also write a `safety_checkin_ok_at` column/flag on the ride row that the loop checks before escalating. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-252 | Minor P2 | Public share-tracking endpoint has no rate limit File: backend/routes/rides/sharing.py:171 Fix: Add the public/api rate-limit decorator (keyed by client IP) to track_shared_ride, mirroring the other ride endpoints. | S (≤½ day) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-253 | Minor P2 | Rating comment has no length bound, allowing arbitrarily large payloads onto the ride row File: backend/schemas.py:420 Fix: Add `max_length=1000` (or similar) to RideRatingRequest.comment. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |

### Workstream: Support & Integrations (14)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-266 | Minor P2 | resolution and refund_amount are unvalidated (arbitrary strings, negative/zero amounts) File: backend/routes/disputes.py:47 Fix: Use Literal["approved","partial_refund","rejected"] for resolution, Field(gt=0) on refund_amount/requested_amount, and compare requested_amount against None rather than falsiness. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-267 | Minor P2 | Duplicate-dispute guard is check-then-insert with no DB constraint File: backend/routes/disputes.py:70 Fix: Add a partial unique index on disputes(ride_id) WHERE status IN ('open','under_review') and handle the conflict as 400, or key the refund idempotency on ride_id. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-268 | Minor P2 | Fire-and-forget Zoho ticket task reference not retained File: backend/routes/disputes.py:109 Fix: Keep the task in a module-level set with a discard done-callback (or use the project's spawn() helper used elsewhere for background sends). | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-269 | Minor P2 | Approved-refund push notification never says 'approved' (compares to nonexistent value 'refund') File: backend/routes/disputes.py:293 Fix: Map labels from the real enum: approved/partial_refund → 'approved', rejected → 'reviewed and declined'. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-270 | Minor P2 | Favorites listed least-used first (order='use_count' without desc) File: backend/routes/favorites.py:49 Fix: Pass desc=True (and consider secondary order by last_used_at). | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-271 | Minor P2 | Favorite duplicate check compares only latitudes, ignoring longitudes File: backend/routes/favorites.py:70 Fix: Include pickup_lng and dropoff_lng in the proximity comparison (all four coordinates within the tolerance). | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-272 | Minor P2 | use_count increment is a non-atomic read-modify-write File: backend/routes/favorites.py:107 Fix: Use a Postgres RPC or SQL `use_count = use_count + 1` (Supabase rpc) instead of client-side arithmetic. | L (~1 week) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-273 | Minor P2 | Unauthenticated /health leaks raw DB exception details and internal loop inventory File: backend/routes/main.py:90 Fix: Return only {status, db: ok¦error} publicly; gate the detailed error string and per-loop breakdown behind admin auth or an internal header. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-274 | Minor P2 | GET unsubscribe executes the opt-out, so mail-scanner link prefetch silently unsubscribes users File: backend/routes/marketing.py:106 Fix: Make the GET render a confirmation page with a button that POSTs to perform the opt-out; keep the RFC 8058 POST behavior unchanged. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-275 | Minor P2 | In-app opt-out suppression misattributed as 'unsubscribe_link' in the CASL audit trail File: backend/routes/marketing.py:163 Fix: Pass source=body.source (rider_app/driver_app) to add_marketing_suppression. | S (≤½ day) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-276 | Minor P2 | /support/chat lacks the AI-specific rate limit and daily cap applied to /ai/chat File: backend/routes/support.py:97 Fix: Apply ai_chat_limit (and ideally the same per-user daily cap) to /support/chat. | S (≤½ day) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |
| SPINR-277 | Minor P2 | Support escalation accepts unbounded message/transcript and has no dedicated rate limit File: backend/routes/support.py:133 Fix: Add Field(max_length=...) caps (e.g. 2000 for message, 20000 for transcript) and a tight rate limit such as 3/minute on the escalation endpoint. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-278 | Minor P2 | Mirror search interpolates user input into PostgREST or_ filter with only commas escaped File: backend/services/zoho_desk_db.py:124 Fix: Sanitize the term to a safe character allowlist (or escape PostgREST reserved characters and LIKE wildcards) before interpolation. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-279 | Minor P2 | OAuth client_secret and refresh_token sent as URL query parameters File: backend/services/zoho_desk_service.py:137 Fix: Send the grant as a form body (`data=params`) — Zoho's token endpoint accepts standard application/x-www-form-urlencoded OAuth2 requests. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |

### Workstream: Safety, Privacy & Reporting (12)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-229 | Minor P2 | spinr_payment_settlement_total emitted with undocumented outcome/label variants File: backend/routes/rides/payments.py:179 Fix: Reconcile the metric contract: either update CLAUDE.md to include the 'already_paid' outcome and standardize the label set (method,outcome[,path]) across both call sites, or map already_paid into the documented enum so exposition is consistent. | L (~1 week) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-230 | Minor P2 | track_ride_requested/completed/payment forward arbitrary dicts to third-party analytics without PII guard File: backend/utils/analytics.py:330 Fix: Apply an allowlist / coordinate-rejection to the ride and payment event payloads the same way track_driver_online rejects lat/lng, so raw GPS or addresses can never reach third-party analytics even if a future caller passes them. | S (≤½ day) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-231 | Minor P2 | PDF receipt has no surge disclosure line or note File: backend/utils/receipt_pdf.py:88 Fix: Add a surge disclosure note (mirroring email_receipt.py) when ride['surge_multiplier'] > 1.0 so the PDF receipt discloses surge like the email does. | S (≤½ day) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-254 | Minor P2 | Client-supplied reported_at stored unvalidated — malformed value 503s the safety report File: backend/routes/safety.py:79 Fix: Parse reported_at with datetime.fromisoformat (fall back to server time on failure) instead of trusting the raw string, and clamp it to a sane window around now. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-255 | Minor P2 | Zoho safety ticket created via unreferenced fire-and-forget task File: backend/routes/safety.py:99 Fix: Hold the task in a module-level set with a done-callback that discards it and logs exceptions (e.g. task.add_done_callback that logs task.exception()). | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-256 | Minor P2 | Consent state change and CASL audit event are non-atomic — audit row can be lost after state changed File: backend/services/marketing_consent.py:87 Fix: Move both writes into a single Postgres function (SECURITY DEFINER, like corporate_wallet_apply_delta) or write the event first and derive/confirm the preference update, so a consent state never exists without its audit event. | L (~1 week) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-257 | Minor P2 | Route-snapshot ledger marked deleted without checking per-object storage.remove results File: backend/utils/retention_purge.py:113 Fix: Intersect the remove() response with the requested paths and only stamp deleted_at for confirmed deletions, leaving the rest for the next daily run. | S (≤½ day) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-258 | Minor P2 | Purge cadence broken: jitter floor (21.6h) under lock TTL (23h) skips daily runs, and the 03:00 scheduler is dead code File: backend/utils/retention_purge.py:306 Fix: Sleep via _seconds_until_next(3) so runs align to 03:00 UTC and are always > lock TTL apart, or drop the lock TTL below the minimum sleep (e.g. 20h). | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-259 | Minor P2 | in_progress query capped at 200 rows with no pagination — rides beyond the cap never get safety check-ins File: backend/utils/safety_checkin_loop.py:80 Fix: Page through results (offset loop or keyset on id) or at minimum order by started_at ascending so the oldest — highest-risk — rides are always included. | M (~2 days) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-260 | Minor P2 | In-memory Redis fallback makes rider 'I'm okay' responses invisible to the loop — false escalations File: backend/utils/safety_checkin_loop.py:130 Fix: Detect fallback mode in redis_client (expose an is_shared() flag) and disable the check-in loop with a loud error when Redis is not actually shared, instead of generating false safety incidents. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-261 | Minor P2 | Partial vendor fetch failures return exit 0 — a permanently broken vendor URL silently drops out of the quarterly audit File: backend/utils/subprocessor_audit.py:141 Fix: Return a non-zero (or at least 1) exit code whenever errors is non-empty, or track consecutive per-vendor failures in the baseline and fail after N misses so the Action opens a PR for review. | S (≤½ day) | Make the guard blocking and add a CI test that fails on a bad input. |
| SPINR-262 | Minor P2 | CASL unsubscribe tokens keyed to JWT_SECRET with no key versioning — secret rotation breaks all outstanding links File: backend/utils/unsubscribe_token.py:52 Fix: Use a dedicated UNSUBSCRIBE_SIGNING_KEY with support for verifying against a list of current+previous keys (key id in the payload), decoupling CASL link validity from JWT secret rotation. | S (≤½ day) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |

### Workstream: Drivers & Insurance Periods (11)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-192 | Minor P2 | Daily/weekly/monthly/comparison earnings use float accumulation and UTC day-bucketing File: backend/routes/drivers/earnings.py:341 Fix: Accumulate with Decimal (serialize via _money_str) and convert ride_completed_at to the driver's service-area timezone before date bucketing. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-193 | Minor P2 | Admin GET /drivers with lat/lng ignores radius and vehicle filters File: backend/routes/drivers/location.py:302 Fix: Apply the same geo-bounds + distance filter used by /nearby (or drop the misleading lat/lng parameters). | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-194 | Minor P2 | Legacy location batch accepts unbounded point lists and out-of-range coordinates File: backend/routes/drivers/location.py:343 Fix: Cap legacy batches (e.g. 500 points) and add ge/le bounds to lat/lng on both models, rejecting out-of-range values. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-195 | Minor P2 | Redundant second drivers-row fetch in the legacy location write hot path File: backend/routes/drivers/location.py:410 Fix: Reuse driver_rows[0] from the first fetch for the mark_present check. | S (≤½ day) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-196 | Minor P2 | Attestation nonce is issued but never stored or verified — replay protection is fictional File: backend/routes/drivers/location.py:419 Fix: Store the nonce (Redis, short TTL, keyed to user) and require/consume it inside verify_device when validating the attestation token. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-197 | Minor P2 | Demand heatmap exposes exact per-ride pickup coordinates to all drivers File: backend/routes/drivers/profile.py:252 Fix: Aggregate to geohash/grid cells with counts (and a minimum count per cell) before returning. | S (≤½ day) | Assert no PII or raw GPS appears in the emitted log/analytics/Sentry payload; add a scrubber test. |
| SPINR-198 | Minor P2 | apply_referral_code has a check-then-write race allowing overwrite of an applied referral File: backend/routes/drivers/referrals.py:196 Fix: Make the update conditional (`{"id": ..., "referral_code_used": None}`) and treat zero rows updated as 'already applied'. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-199 | Minor P2 | rate_rider allows rating before completion and unlimited overwrites File: backend/routes/drivers/ride_cancel.py:371 Fix: Require ride.status == completed and reject (or version) re-rating once rider_rating is set. | S (≤½ day) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-200 | Minor P2 | Client-supplied naive captured_at timestamps can 500 the completed-ride retention check File: backend/routes/drivers/ride_complete.py:96 Fix: Normalize captured_at to UTC-aware in a validator (assume UTC when naive, or reject naive timestamps with 422). | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-201 | Minor P2 | arrive_at_pickup is not retry-idempotent despite the declared idempotency contract File: backend/routes/drivers/ride_flow.py:589 Fix: On guard failure, re-read the ride and return success if it is already driver_arrived for this driver (same pattern as accept's duplicate handling). | M (~2 days) | Add a component or store test covering the error/empty/loading state; snapshot the corrected copy. |
| SPINR-202 | Minor P2 | No CSV formula-injection escaping in DSAR export cells File: backend/routes/drivers/tax_exports.py:323 Fix: Prefix cells starting with =, +, -, @ with a single quote (standard CSV-injection mitigation). | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |

### Workstream: Auth & Identity (10)

| ID | Severity | Finding & fix approach | Effort | Test to add |
| --- | --- | --- | --- | --- |
| SPINR-151 | Minor P2 | Synchronous firebase_admin App Check verification inside async middleware blocks the event loop on every production /api request File: backend/core/middleware.py:193 Fix: Run verification off-loop: `await loop.run_in_executor(None, app_check.verify_token, token)`, and/or pre-warm + refresh the JWKS in a background task so the request path only does in-memory signature checks. | M (~2 days) | Add a benchmark or assertion (e.g. single DB round-trip); compare against the perf baseline. |
| SPINR-152 | Minor P2 | CSRF rejection logs use printf-style placeholders with loguru — method/path/origin are silently dropped from the log line File: backend/core/middleware.py:392 Fix: Switch to loguru brace formatting: `logger.warning("CSRF token missing: {} {}", request.method, path)` and `logger.opt(exception=True).warning("Failed to evict corrupt cache key {}", key)`. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-153 | Minor P2 | Production CORS always allows http://localhost:3000 and :3001 with credentials File: backend/core/middleware.py:578 Fix: Only append the localhost entries when settings.ENV != 'production' (dev origins already come from the ALLOWED_ORIGINS default in config.py, so the production list should contain only real deployed origins). | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-154 | Minor P2 | Global exception handler logs unhandled 500s without a traceback and drops HTTPException headers File: backend/core/middleware.py:650 Fix: Use `logger.opt(exception=exc).error(...)` (loguru) so the traceback is captured (and reaches Sentry via the ERROR sink), and pass `headers=getattr(exc, "headers", None)` through to the rebuilt JSONResponse. | S (≤½ day) | Assert the metric name/labels or receipt line matches the documented contract in CLAUDE.md. |
| SPINR-155 | Minor P2 | $regex terms inside $or clauses do not escape SQL LIKE wildcards, unlike the top-level $regex path File: backend/repositories/_base.py:503 Fix: Apply _escape_like to the $regex value before _postgrest_pattern in _build_or_clause_term so both filter paths neutralize `%` and `_` identically. | S (≤½ day) | Add a unit test reproducing the bad input then asserting corrected output; add a ride-state-machine case if a transition is involved. |
| SPINR-156 | Minor P2 | /metrics accepts the auth token as a URL query parameter, leaking it into access logs File: backend/server.py:243 Fix: Accept the token only via the Authorization header (Prometheus, Grafana Agent and Railway scrapers all support bearer-token config); if a query param must be kept for a legacy scraper, document the exposure and rotate the token regularly. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-157 | Minor P2 | Full auth router mounted at App-Check-exempt /api/portal and triple-mounted overall — OTP quotas tripled and App Check on auth is bypassable File: backend/server.py:351 Fix: Mount a restricted sub-router at /api/portal containing only the endpoints the browser portal needs (send-otp/verify-otp/send-email-otp/verify-email-otp/refresh/logout), and key OTP rate limits on a normalized scope (strip the mount prefix) or on the destination phone so multiple mounts share one bucket. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-158 | Minor P2 | Rate-limit client IP trusts spoofable CF-Connecting-IP / X-Real-IP with no origin lockdown in place File: backend/utils/rate_limiter.py:100 Fix: Add an origin-authentication check: require a Cloudflare Authenticated Origin Pull cert or a shared-secret header injected by a Cloudflare Transform Rule, and fall back to the socket peer IP (ignoring CF-Connecting-IP) when that proof is absent. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-159 | Minor P2 | AsyncLimiter default_limits (100/min, 1000/hr) are never applied — undecorated endpoints have no rate limit at all File: backend/utils/rate_limiter.py:113 Fix: Either add a lightweight global middleware that runs the default limits for any request not already checked (mirror slowapi's middleware behaviour), or delete the default_limits argument and document that every route must carry an explicit limiter decorator, enforced by a CI check that scans route definitions. | S (≤½ day) | Add tests for both the allowed and the denied path; assert 403 / ownership / signature rejection. |
| SPINR-160 | Minor P2 | redis_set_nx fails OPEN on Redis errors — every replica acquires the 'leader lock' during a Redis outage File: backend/utils/redis_client.py:159 Fix: Make redis_set_nx consistent with the module's fail-loud policy: when a Redis URL is configured and the call errors, either raise or return False (treat as 'lock not acquired'), and log at ERROR. Returning False is the safe default for leader election — skipping one tick beats duplicating side-effects. | S (≤½ day) | Add/extend a fare-settlement or wallet regression test asserting the corrected amount; run the payments/fare suite (90% coverage target). |

## Testing strategy (applies to every item)

- Backend: pytest with @pytest.mark.anyio for async; mock Supabase via the mock_supabase_client fixture; patch backend.db_supabase.supabase. Coverage floors: payments/fare/crypto ≥90%, rides/dispatch ≥80%, admin/utils ≥70%.

- Every new state transition adds a case to test_ride_state_machine.py; every fare branch and every auth/RLS path (allowed AND denied) gets a test.

- Mobile / web: Jest (apps) and Vitest (admin) for the corrected error, empty, and loading states; snapshot corrected copy; Playwright E2E for admin flows.

- No fix merges without the regression test named in its row above.

## Rollout & safety

- Background-loop changes must stay replay-safe (atomic DB claim, idempotency key, or claim flag) — they run on every replica simultaneously.

- Schema changes go in a NEW migration (append-only, next free NN), ship RLS in the same file, and are safe against live traffic (batched long updates).

- Deploy to Fly.io (primary) and Railway (standby) in parallel from main; money-touching changes get a staged rollout and reconciliation watch.

- Wrap risky behavioural changes (e.g. the shared leader-lock fail-closed fix) behind a flag so they can be reverted without a redeploy.

## Definition of done (per item)

- The cited defect no longer reproduces (demonstrated by the new test).

- A regression test is added and passing in CI.

- The change is scoped to one logical fix (≤ ~200 line diff) with a clear commit.

- Any CLAUDE.md convention the finding violated is now satisfied.

- For money/auth/safety items: a second reviewer sign-off.